## Test matrix
SCRUM-24 QA Test Matrix — frozen v3
Test ID | Area | Case type | Input and procedure | Expected outcome | Evidence required | Dependency / source | Initial scope
QA-01 | Character labels | Normal / boundary | Inspect the loader mapping at indices 0, 9, 10 and 35, and the full retained label set. Inspect the lowercase filtering step. | Labels 0-35 map to 0123456789ABCDEFGHIJKLMNOPQRSTUVWXYZ. All 36 classes are retained; lowercase labels 36-61 are excluded. | Mapping output, retained class counts and code reference. | SCRUM-10; loader and public EMNIST data | Initial data review
QA-02 | Image orientation | Normal | Use known EMNIST samples of asymmetric characters such as F, L and 2. Compare raw images with loader output and a manually verified upright reference. | Loaded images are upright, not mirrored or rotated. Do not rely only on an assertion that a transpose was applied. | Before/after image with sample IDs and manual orientation assessment. | SCRUM-10; audit outputs or reproducible run | Initial data review
QA-03 | Splits and leakage | Normal / invalid | Repeat the split with seed 6642. Compare membership. Check synthetic test-log source IDs and exact-image duplicates against train and validation. | Repeated membership is identical. Test logs use only eligible EMNIST test images, excluding exact images duplicated in train/validation. Verify generator source IDs against this pool. | Split membership/seed and leakage output; generator source-ID record when available. | SCRUM-11 and SCRUM-9; public character data | Initial data review
QA-04 | Cell extraction | Normal | Use a clean synthetic odometer field containing 048213. Run registration and cell extraction; inspect boxes and ordered crops. | Six ordered crops correspond one-to-one to the six characters. Crop-count success alone is insufficient if characters are cut off. | Input image, extraction overlay and six labeled crops. | SCRUM-13; synthetic image and box ground truth | As component becomes available
QA-05 | Cell extraction | Invalid | Remove one character from a synthetic six-character field. Compare extraction with ground truth before scoring the classifier. | Record the empty crop separately from recognition errors. Preserve the incomplete value and send the affected reading to review under the documented configuration. | Input, crops and separate segmentation failure record. | SCRUM-8/13/15; controlled missing-character fixture; D3 | As component becomes available
QA-06 | Field assembly | Normal / boundary | Inject known character sequences into assembly: RC5107, 092726, 0921, KMR, 048213, 048238, 025 and 0038. | Characters stay in order; leading zeros are preserved. Field lengths and letter/digit positions match SCRUM-8 and the ML-7 specification. Raw values remain available. | Injected predictions and assembled field values. | SCRUM-8/15; documented field specification | As component becomes available
QA-07 | Allowed character sets | Boundary | At a digit position, supply scores favoring O over 0. At a letter position, reverse that ordering. Exercise the documented per-position output restriction method. | Digit positions return only 0–9; capital-letter positions only A–Z. The current approach already documents this method. This controlled selection check does not measure model accuracy. | Input scores, field type and selected character. | SCRUM-8/14/15; documented field restriction | As component becomes available
QA-08 | Reference checks | Normal | Use baseline B1 and its made-up HR list and visit schedule. Run employee and client/date reference checks. | RC5107 exists in the made-up HR fixture; KMR/PDL match the made-up schedule on 09/21/26. These mock reference checks pass. No external reference-data integration is claimed. | Reference fixture, parsed row and check flags. | SCRUM-8/16; synthetic B1 reference fixture | As component becomes available
QA-09 | Employee lookup | Invalid | Change only the baseline employee ID to ZZ9999, which is absent from the synthetic HR list. | Employee check fails; affected reimbursement is not auto-posted and needs review with an explicit employee reason. | Fixture, lookup result, flags and routing output. | SCRUM-8/16; synthetic HR; current review configuration | As component becomes available
QA-10 | Client lookup | Invalid | Change only the first baseline client code to XYZ, absent from RC5107's schedule for 09/21/26. | Client/date check fails for that row; it routes to review with a reason. A valid-looking three-letter code is not enough. | Synthetic schedule, input row, check flags and route. | SCRUM-8/16/22; synthetic visit schedule | As component becomes available
QA-11 | Dates | Normal | With evaluation date fixed at 10/05/26, use week ending 09/27/26 and trip date 09/21/26. | Week ending is a valid recent Sunday. Trip date is valid and within the stated week. Date checks pass. | Fixed evaluation date, input values and flags. | SCRUM-8/16; stated date requirements | As component becomes available
QA-12 | Dates | Invalid | Compare a valid 0228 control with an impossible 0230 trip date. Keep the week ending and employee valid; inspect the date flag and review route. | February 30 is rejected as an invalid date. Do not silently roll it into March; route the affected row to review. | Raw date, validation reason and route. | SCRUM-16/22 | As component becomes available
QA-13 | Dates | Invalid | For week ending 09/27/26, set the trip to 0928. Include that date/client in the synthetic schedule and inspect date validation and dependent lookup behavior. | The trip is outside the submitted week and requires review even though a matching schedule entry exists. Record any dependent client-lookup failure separately. | Fixture, schedule and week-check result. | SCRUM-8/16/22 | As component becomes available
QA-14 | Date boundaries | Boundary | Test Monday/Sunday week endpoints, adjacent outside dates and year rollover. For the 60-day boundary, use Sunday 08/02/26 with evaluation dates 09/30/26, 10/01/26 and 10/02/26 (59, 60 and 61 days old). | The documented week is Monday–Sunday, inclusive. Dates exactly 60 days old are permitted; 61 days are rejected. Infer the trip year from the submitted week and run each listed variant. | Fixed evaluation dates and per-variant expected/actual values, including year rollover. | SCRUM-8/16; documented date interpretation; D1 | As component becomes available
QA-15 | Odometer increase | Invalid / boundary | Run two isolated variants: end equals start; end is less than start. Keep other reference inputs valid. | Both fail end > start. Preserve original readings and route to review. Record both variants before marking this case Passed. | Both input pairs, arithmetic flags and routes. | SCRUM-17/22 | As component becomes available
QA-16 | Odometer continuity | Boundary / invalid | With prior end 048238, test next start 048238 and then 048237. Make each new row's end and miles internally consistent. | Equality passes continuity; 048237 fails because it moves backward. The failed variant requires review. Record results for both. | Ordered rows, continuity flags and route. | SCRUM-17/22 | As component becomes available
QA-17 | Written miles | Invalid | Use start 048390, end 048437 and written miles 042. Treat these as correctly read fields for this rule test. | Difference is 47, not 42. Miles check fails; original 042 is retained and the row needs review. This is a source inconsistency, not a recognition error. | Input values, computed 47, discrepancy flag and route. | SCRUM-17/22; instructor Figure 1 example | As component becomes available
QA-18 | Weekly total | Invalid | Use baseline rows of 025 and 013 miles, but change only total miles from 0038 to 0039. | Sum is 38; the written total 0039 fails reconciliation and is preserved. Current settings send both rows to review. Record the total flag and row routes. | Rows, sum, total flag and routing scope. | SCRUM-8/17; current total-mismatch handling; D3 | As component becomes available
QA-19 | Arithmetic and reimbursement | Normal | Use baseline B1. Check both row differences, continuity, written total and reimbursement at $0.62 per mile. | Differences are 25 and 13; total is 38. Row amounts are $15.50 and $8.06; combined amount is $23.56. These passes alone do not establish auto-post eligibility. | Arithmetic outputs, amounts and flags. | SCRUM-17; B1 fixture | As component becomes available
QA-20 | Review routing | Invalid | Use the QA-17 discrepancy with supplied confidence 0.99, above the configured prototype thresholds. Test routing after the failed business check. | A failed business check forces review despite high confidence. Output includes the failure reason. Confidence cannot override the discrepancy. | Confidence input, failed flag and explicit review decision. | SCRUM-8/22; D2 for final threshold decision | As component becomes available
QA-21 | Confidence and high-impact review | Boundary / prototype policy | A: Test below/equal/above 0.82 ordinary and 0.92 for each first-three odometer position with valid business checks. B: Check digit-place cost calculations at $0.62/mile; keep the $100 example separate from routing. | Below confidence threshold requires review; equality meets it if all other checks pass. Failed checks and crop warnings override confidence. Standalone cost labels are sensitivity examples. A $100 routing cutoff is not part of frozen v3. | QA21_Confidence_Boundaries.json; QA21_Reimbursement_Analysis.json; QA21_Status.json; Regression_Test_Log.txt. Production calibration/approval is outside this acceptance check. | Frozen reader_policy.json; docs/routing_policy.md; SCRUM-19 standalone calculation | As component becomes available
QA-22 | Image conditions | Normal / degraded | Read the 18 SCRUM-9 images and all 36 SCRUM-26 images with their saved answers, case-specific references and date 2026-10-05. Record each pack separately; 18 images overlap. | Report characters, fields, rows, extraction, recognition, review routes and invalid-source auto-posts. Validate known values separately. Compare paired conditions; no accuracy cutoff. Repeated fixtures do not establish generalization. | Synthetic_Form_Metrics.json; QA_Fixture_Metrics.json; both known-value reports; 18 synthetic_form_results and 36 qa_fixture_results responses. | SCRUM-9 and SCRUM-26; frozen v3 checkpoint and current per-case references | As component becomes available
Fixture B1 and execution rules
Fixture B1 | B1 is a controlled fixture implemented in notebook Step 10. HR and visit-schedule records are synthetic/mock. Reference date 10/05/26; employee RC5107; week ending 09/27/26. No external reference integration is claimed.
B1 rows | 09/21/26 KMR: 048213 to 048238, miles 025. 09/21/26 PDL: 048238 to 048251, miles 013. Written total 0038. Both clients appear on this employee's synthetic schedule.
Single-fault variants | Known-value variants cover each rule. Step 19 checks date/confidence boundaries. Steps 21–22 read both fixture packs separately; SCRUM-26 image coverage is now included.
Actual results | Execution log records the new frozen-v3 run and exact checkpoint. Historical execution evidence remains under archive/ff674684. No model training or reader/policy changes occurred.
Variants | Where one test includes multiple variants, report each in the actual result/evidence or append one execution row per variant. Passed requires all listed variants to pass.
Failure classification | Data, segmentation, recognition, assembly, validation, routing, environment or mixed. A bad crop is not automatically a classifier error.
Scope | SCRUM-24 covers the plan and available checks. QA owns SCRUM-9/24/26/27. Ish owns SCRUM-18 model evaluation; Giuseppe owns SCRUM-33 photographed handwritten forms.
Story acceptance | SCRUM-24 covers representative cases, expected outcomes, evidence expectations and available-check results. Its week-one scope explicitly permits unavailable checks to remain pending.
Requirement clarifications and remaining actions
ID | Related SCRUM(s) | Topic | Current basis and remaining action
D1 | SCRUM-8 | Documented date rules | QA-14 passed 11/11 variants for the documented Monday–Sunday week, inclusive day 60 and year rollover. No additional data is needed for these checks. Evidence: QA14_Date_Boundaries.json.
D2 | SCRUM-19 and SCRUM-22 | Confidence and high-impact policy | QA-21 passed 21/21 configured confidence boundaries and 6/6 digit-cost calculations. The frozen policy uses 0.82/0.92 confidence thresholds. The $100 sensitivity example is not a routing requirement. Production calibration and payment approval remain future work.
D3 | SCRUM-8 and SCRUM-22 | Documented review behavior | Frozen behavior: missing characters require row review; an invalid employee or mismatched total requires review of all rows. QA-05, QA-09 and QA-18 pass. Configured confidence boundaries pass QA-21; production calibration is not established.
D4 | SCRUM-33 and SCRUM-18 | Synthetic evaluation and separate handwriting scope | QA-22 records the 18 SCRUM-9 images and 36 SCRUM-26 images separately; 18 images overlap. Paired controls reuse handwriting. The 12 photographed forms are a separate repeated benchmark in docs/results_summary.md; this QA run does not claim fresh handwriting generalization.

## Execution log
Frozen v3 execution log — 2026-10-07
Test ID | Status | Failure category | Actual result / blocker | Evidence file or link | Command / procedure and fixture / conditions | Tester | Execution date
QA-01 | Passed | None | All 36 labels map to 0–9 and A–Z; lowercase labels excluded. Train 480,595; validation 53,398; test 89,264. Label check only, not accuracy. | Step 3; QA01_Label_Check.json; notebook mapping and category output. | Step 3: read_mapping and load_split for train, val and test. Inspect boundaries 0, 9, 10 and 35 and all retained classes. | Codex (automated QA) | 2026-10-07
QA-02 | Passed | None | Nine displayed samples (three each of F, L and 2) are upright and correctly facing after correction; dimensions remain 28 × 28. Visual sample check only. | Step 4; QA02_Orientation_Check.png; QA_Visual_Review.json. | Step 4: seed 6642. IDs F: 532542, 343313, 429025; L: 613511, 515928, 276656; 2: 686511, 643656, 219853. Compare before/after images visually. | Codex (automated QA) | 2026-10-07
QA-03 | Passed | None | Repeat membership is identical and disjoint. Two exact test/train matches (test-array indices 75979, 83597) are excluded. Eligible pool: 89,262. All 148 positions in one generated six-row log use eligible test sources with matching labels. Near-duplicates were not assessed. | Steps 5–8; QA03_Duplicate_Check.json; QA03_Generator_Pool_Check.json; QA03_Generator_Source_Check.json; qa03_generated_logs/. | Steps 5–8: repeat seed 6642; check intersections, coverage and exact duplicates; verify pool exclusions; generate one clean six-row log and check every source/label. | Codex (automated QA) | 2026-10-07
QA-04 | Passed | None | One clean 048213 field produces six ordered, distinct crops and six 28 × 28 normalized images. Visual review found no missing digits, clipping or neighboring digits in these crops. Extraction only; no classifier accuracy claim. | Step 16; QA04_Input.png; QA04_Character_Crops.png; QA04_Character_Crops_Check.json; QA_Visual_Review.json. | Step 16: seed 6642, clean condition. Register the synthetic image, extract rows.1.odometer_start, compare six crops with known characters and saved boxes. | Codex (automated QA) | 2026-10-07
QA-05 | Passed | None | Removing the third character produces an empty crop and cell_extraction failure. Assembly retains 04?213 without a complete value; the row needs review. Other five readings are supplied. The missing-character variant meets the specified case. | Steps 17–18; QA05_Missing_Character_Input.png; QA05_Missing_Character_Check.png and .json. | Step 17: restore third box from blank template; run extraction and empty-cell handling; inject the other readings at 0.99; assemble and validate B1. Step 18 saves inputs. | Codex (automated QA) | 2026-10-07
QA-06 | Passed | None | All eight injected sequences assemble in order with leading zeros retained: RC5107, 092726, 0921, KMR, 048213, 048238, 025 and 0038. | Step 9; QA06_Field_Assembly_Check.json. | Step 9: inject known characters into assemble_field; compare complete raw values and expected lengths. No model recognition involved. | Codex (automated QA) | 2026-10-07
QA-07 | Passed | None | With supplied O/0 scores, the actual predictor selects 0 in a digit field and O in a letter field. Returned alternatives respect the allowed character set. This checks the documented selection method, not recognition accuracy. | Step 15; QA07_Allowed_Characters_Check.json. | Step 15: override only probability generation; use scores 0.60/0.40 and the project predictor with digit/letter restrictions. This is a selection-rule check, not model accuracy. | Codex (automated QA) | 2026-10-07
QA-08 | Passed | None | B1 employee RC5107 exists in the synthetic HR fixture; KMR and PDL match its made-up visit schedule for 09/21/26. All mock reference checks pass. No external HR/schedule integration was tested. | Step 10; QA_Baseline_Validation_Check.json. | Step 10: validate B1 using made-up HR/schedule data, evaluation date 10/05/26 and supplied readings at confidence 0.99. | Codex (automated QA) | 2026-10-07
QA-09 | Passed | None | Unknown employee ZZ9999 fails the mock employee check and sends both rows to review with an employee reason. Dependent client checks also fail. This verifies the current documented configuration. | Step 11; QA_Invalid_Reference_Check.json. | Step 11, employee variant: replace B1 employee only, validate against unchanged synthetic references and inspect flags/routes. | Codex (automated QA) | 2026-10-07
QA-10 | Passed | None | Client XYZ is absent from the synthetic schedule: first-row client/date lookup fails and the row needs review. The unchanged second row remains auto-post eligible under the prototype policy. External reference integration was not tested. | Step 11; QA_Invalid_Reference_Check.json. | Step 11, client variant: replace first B1 client only; inspect each row’s lookup flag, reason and route. | Codex (automated QA) | 2026-10-07
QA-11 | Passed | None | Week ending 09/27/26 and trip date 09/21/26 pass the normal date checks with evaluation date 10/05/26. Boundary policy is not established by this normal case. | Step 10; QA_Baseline_Validation_Check.json. | Step 10: run B1 with a frozen evaluation date and inspect week-ending and trip-date flags. | Codex (automated QA) | 2026-10-07
QA-12 | Passed | None | Valid 0228 control passes; 0230 is retained and rejected, with the row sent to review. Implementation combines calendar validity and week membership; the dependent client lookup also fails. An independent calendar-only flag was not tested. | Step 12; QA_Invalid_Date_Check.json. | Step 12: one-row control dated 02/28/26, week ending 03/01/26, evaluated 03/02/26; mutate date to 0230 and inspect combined date flag and route. | Codex (automated QA) | 2026-10-07
QA-13 | Passed | None | Trip 0928 is rejected for week ending 09/27/26 and needs review even though the synthetic schedule includes the date/client. The combined date check fails; its dependent client lookup also fails. | Step 12; QA_Invalid_Date_Check.json. | Step 12: use B1 with first trip 0928 and a matching 09/28/26 KMR schedule entry; inspect combined date flag, dependent lookup and route. | Codex (automated QA) | 2026-10-07
QA-14 | Passed | None | 11/11 variants pass: Monday/Sunday included; adjacent outside dates rejected; 59/60-day ages allowed and 61 rejected; four December/January rollover dates resolve to the correct year. Fixed dates and known readings test current documented behavior, not recognition. | Step 19; QA14_Date_Boundaries.json: all 11 expected/actual variants. | Step 19: four week endpoints/outside dates, three 59/60/61-day variants and four year-rollover dates. Valid synthetic references and supplied 0.99 confidence. | Codex (automated QA) | 2026-10-07
QA-15 | Passed | None | Both end=start (048213) and end<start (048212) fail the increase rule and need review. Original readings remain available. Written-mile equality also fails in these deliberately inconsistent inputs. | Step 13; QA_Odometer_Check.json. | Step 13: one B1 row starting 048213; separately set end to 048213 and 048212. Inspect both flags/routes. | Codex (automated QA) | 2026-10-07
QA-16 | Passed | None | Next start 048238 equal to prior end passes continuity. Next start 048237 fails continuity and needs review. Other mileage values were adjusted to remain internally consistent in each variant. | Step 13; QA_Odometer_Check.json. | Step 13: B1 first end 048238; test second starts 048238 and 048237 with consistent second-row miles and totals. | Codex (automated QA) | 2026-10-07
QA-17 | Passed | None | 048437 − 048390 = 47 differs from written 042. The miles-equality check fails, original 042 is retained and the row needs review. Controlled source inconsistency, not a model recognition error. | Step 14; QA_Mileage_Discrepancy_Check.json. | Step 14: one row with start 048390, end 048437, written miles 042 and total 0042; validate supplied readings at confidence 0.99. | Codex (automated QA) | 2026-10-07
QA-18 | Passed | None | Rows sum to 38, but written total 0039 is preserved and flagged. Both rows need review under the current total-mismatch setting. Individual row arithmetic remains valid. | Step 14; QA_Mileage_Discrepancy_Check.json. | Step 14: change B1 total only from 0038 to 0039; inspect total flag and both routes. | Codex (automated QA) | 2026-10-07
QA-19 | Passed | None | B1 differences are 25 and 13; continuity and written total 38 pass. At $0.62/mile, reimbursements are $15.50 and $8.06, totaling $23.56. | Step 10; QA_Baseline_Validation_Check.json. | Step 10: validate B1, inspect arithmetic/total flags, and compare row and combined reimbursement amounts. | Codex (automated QA) | 2026-10-07
QA-20 | Passed | None | The QA-17 discrepancy requires review at supplied confidence 0.99, above configured thresholds 0.82/0.92. Failed business checks override high confidence. This verifies the prototype behavior; it does not establish final threshold calibration or approval under SCRUM-22. | Step 14; QA_Mileage_Discrepancy_Check.json. | Step 14: use the QA-17 variant with 0.99 supplied character confidence; inspect failed miles flag and explicit review route. | Codex (automated QA) | 2026-10-07
QA-21 | Passed | None | Frozen policy checks passed: 21/21 confidence variants and 6/6 standalone cost calculations. Ordinary/high-place thresholds remain 0.82/0.92. The $100 sensitivity example is not enforced by the reader. Production confidence calibration and payment approval are not established. | Step 19; QA21_Confidence_Boundaries.json; QA21_Reimbursement_Analysis.json; QA21_Status.json; Regression_Test_Log.txt. | Run the unchanged prototype confidence boundaries and standalone calculations. The 41 regression tests also check preprocessing warnings and fail-closed routing. No reader change or production approval is implied. | Codex (automated QA) | 2026-10-07
QA-22 | Evaluated | Recognition | SCRUM-9: 2590/2664 characters (97.22%); 526/594 fields; 60/108 rows. Known values 18/18; invalid-source auto-posts 0. SCRUM-26: 5222/5328 characters (98.01%); 1089/1188 fields; 139/216 rows; known values 36/36; invalid-source auto-posts 0. Packs overlap by 18 images. No accuracy cutoff or generalization claim. | Steps 20–22; Model_Evaluation_Run.json; Synthetic_Form_Metrics.json; QA_Fixture_Metrics.json; Synthetic_Dataset_Validation_Check.json; QA_Fixture_Known_Value_Check.json; saved per-image responses. | Verified the saved frozen checkpoint without training; read 18 and 36 images separately, using each case’s reference file and date 2026-10-05. All three conditions reuse underlying forms. Execution identity and source hashes are in QA_Execution_Record.json. | Codex (automated QA) | 2026-10-07